## Task
Deliverables | Sub Task ID | Task ID | Task Type | Task Name | Description/Detail | Priority | Estimated Start Date | Estimated Completion Date | Actual Completion Date | Status | Assign To | Estimated Person Hr | Actual Person Hr | time axis 2020-05-24 to 2020-07-18
02Hyd06FS | 1.1 | 02Hyd06FS_1.1 | Design/Analysis/Annexes | Penstock Thickness Check | Thickness Calculation Revision as per Khem SIr Update | Urg&Imp | 2020-05-25 | 2020-05-25 | 2020-05-25 | Complete | Ishwar Dahal |  | 3 | 2020-05-25: 3
02Hyd06FS | 1.2 | 02Hyd06FS_1.2 | Drawings | Tender Drawings Update | HM Drawings Update, Thickness and Groove Update in HM Tender Drawings | Urg&Not-Imp | 2020-05-25 | 2020-05-25 | 2020-05-25 | Complete | Ishwar Dahal |  | 4 | 2020-05-25: 4
02Hyd04FS | 1.3 | 02Hyd04FS_1.3 | Report Writing | Update of Tender Documents | Changes as per HM Drawings Update | Urg&Imp | 2020-05-26 | 2020-05-26 | 2020-05-26 | Complete | Ishwar Dahal |  | 3 | 2020-05-26: 3
02Hyd05FS | 1.4 | 02Hyd05FS_1.4 | Report Writing | Update of Tender Documents | Changes as per HM Drawings Update | Urg&Imp | 2020-05-26 | 2020-05-26 | 2020-05-26 | Complete | Ishwar Dahal |  | 2 | 2020-05-26: 2
02Hyd06FS | 1.5 | 02Hyd06FS_1.5 | Report Writing | Update of Tender Documents | Changes as per HM Drawings Update | Urg&Imp | 2020-05-26 | 2020-05-26 | 2020-05-26 | Complete | Ishwar Dahal |  | 1 | bar: 2020-05-26
02TrL07FS | 1.6 | 02TrL07FS_1.6 | Report Writing | Update of Tender Documents | Changes as per HM Drawings Update | Urg&Imp | 2020-05-26 | 2020-05-26 | 2020-05-26 | Complete | Ishwar Dahal |  | 2 | 2020-05-26: 2
02Hyd11FS | 1.7 | 02Hyd11FS_1.7 | Report Writing | Update of Tender Documents | Changes as per HM Drawings Update | Urg&Imp | 2020-05-26 | 2020-05-26 | 2020-05-26 | Complete | Ishwar Dahal |  | 1 | bar: 2020-05-26
02Hyd04FS | 1.8 | 02Hyd04FS_1.8 | Report Writing | Update of Dates on Entire Documents | May to June Date Convert and Compilation | Urg&Imp | 2020-06-01 | 2020-06-02 | 2020-06-02 | Complete | Ishwar Dahal |  | 5 | 2020-06-01: 3; 2020-06-02: 2
02Hyd09DS | 1.9 | 02Hyd09DS_1.9 | Review | External Coordination Meeting / Preparation for Discussion | Coordination with Swayambu Sir and Sunil Sir regarding SGHP Detail Design | Imp&Not-Urg | 2020-06-03 | 2020-06-03 | 2020-06-03 | Complete | Ishwar Dahal |  | 7 | 2020-06-03: 7
02Hyd09DS | 1.1 | 02Hyd09DS_1.1 | Design/Analysis/Annexes | Design Flood Calculations and Update | Review of previous Calculations and additional calculation for MHSP Method | Urg&Imp | 2020-06-11 | 2020-06-11 | 2020-06-11 | Complete | Ishwar Dahal |  | 3 | 2020-06-11: 3
02Hyd09DS | 1.11 | 02Hyd09DS_1.11 | Design/Analysis/Annexes | Update of Hydraulic Design Sheet for Weir Design | Update as per primary and secondary weir in Headworks / Update as per drawing ings update is required | Urg&Imp | 2020-06-11 | 2020-06-11 |  | In Progress | Ishwar Dahal |  | 4 | 2020-06-11: 2; 2020-06-12: 2
02Hyd09DS | 1.1 | 02Hyd09DS_1.1 | Review | Print Review and Check | Final Tender Documents Check and Review | Urg&Imp | 2020-06-09 | 2020-06-10 | 2020-06-10 | Complete | Ishwar Dahal |  | 7 | 2020-06-09: 6; 2020-06-10: 1
04Hyd09DS | 1.1 | 04Hyd09DS_1.1 | Review | Coordination | Coordinate with Swayambu Sir, Sunil Sir and Team Member | Urg&Imp | 2020-05-24 |  |  | In Progress | Ishwar Dahal |  | 7 | 2020-05-24: 7
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Construction Drawings Update | Updates and Detailing of Weir and Stilling basin,Expansion Joint as per Rajesh Sir Comments | Urg&Imp | 2020-05-24 | 2020-05-25 | 2020-05-28 | Sent for External Review | Kabita Shrestha | 7 | 15 | 2020-05-24: 4.5; 2020-05-25: 2; 2020-05-26: 5; 2020-05-27: 1.5; 2020-05-28: 2
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Reinforcement Drawing | Update of reinforcement Weir,Flood wall and Stilling basin rev-01 as per RS Comments and Discussion with team | Urg&Imp | 2020-06-07 | 2020-06-15 |  | Stopped | Kabita Shrestha |  | 14.5 | 2020-05-25: 3; 2020-06-09: 6.5; 2020-06-10: 3.5; 2020-06-11: 1.5
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Reinforcement Drawing | Update of reinforcement drawing of Gravel trap and flushing culvert rev-01 | Urg&Imp | 2020-06-11 | 2020-06-12 |  |  | Kabita Shrestha |  | 4 | 2020-06-11: 3; 2020-06-12: 1
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Literature Review | Study of Expansion joint along with shear key | Urg&Imp | 2020-05-24 |  |  | In Progress | Kabita Shrestha |  | 1.5 | 2020-05-25: 1; 2020-05-26: 0.5
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Review of Construction Drawing | Review of Construction Drawing(LEKHP_52_C01-C04,C07-C08) | Urg&Imp | 2020-05-24 | 2020-05-27 | 2020-05-27 | Complete | Kabita Shrestha |  | 4 | 2020-05-25: 1; 2020-05-28: 3
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Review of Construction Drawing | Review of Construction Drawing(LEKHP_52_C09-C11) | Urg&Imp | 2020-05-24 | 2020-05-27 | 2020-05-24 | Complete | Kabita Shrestha |  | 5 | 2020-05-26: 1.5; 2020-05-27: 3.5
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Review of Construction Drawing | Review of Construction Drawing(LEKHP_51_C01-C08) | Urg&Imp | 2020-05-24 | 2020-05-27 | 2020-05-25 | Complete | Kabita Shrestha |  | 5 | 2020-05-27: 2; 2020-05-28: 0.5; 2020-05-29: 2.5
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Review of Construction Drawing | Review of Settling basin (LEKHP_53_C01-C06) | Urg&Imp | 2020-05-24 | 2020-05-27 | 2020-05-26 | In Progress | Kabita Shrestha |  | 5 | 2020-05-29: 4; 2020-05-31: 1
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Coordination | Coordination with team member | Urg&Imp | 2020-05-31 |  |  |  | Kabita Shrestha |  | 11 | 2020-05-24: 2.5; 2020-05-28: 1.5; 2020-05-31: 2.5; 2020-06-01: 2; 2020-06-03: 0.5; 2020-06-04: 0.5; 2020-06-05: 1.5
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Construction Drawing Update | Update plan in all Construction drawing | Urg&Imp | 2020-05-31 | 2020-06-04 | 2020-06-04 | Complete | Kabita Shrestha |  | 9 | 2020-05-31: 3.5; 2020-06-01: 2; 2020-06-03: 1.5; 2020-06-04: 2
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Construction Drawing Check | Review drawing to check the corrections made after comments(LEKHP-52-C01,C09-C15),53-C01-C06 | Urg&Imp | 2020-05-31 | 2020-06-03 | 2020-06-03 | Complete | Kabita Shrestha |  | 6 | 2020-06-01: 3; 2020-06-02: 2; 2020-06-03: 1
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Construction Drawings Update | Updates and Detailing of Spillway as per RS CommentsLEKHP-952-C01-C03,C08-C10) | Urg&Imp | 2020-06-02 | 2020-06-03 | 2020-06-03 | Complete | Kabita Shrestha |  | 7 | 2020-06-02: 4; 2020-06-03: 3
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Hydraulic Design | Design of Spillway and discussion with RS | Urg&Imp | 2020-06-02 | 2020-06-02 | 2020-06-02 | Complete | Kabita Shrestha |  | 4.5 | 2020-06-02: 1; 2020-06-12: 3.5
04Hyd09DS | 1.2 | 04Hyd09DS_1.2 | Drawings | Drawing Compilation | Compiled Headwork Drawings | Urg&Imp | 2020-06-04 | 2020-06-04 | 2020-06-04 | Complete | Kabita Shrestha |  | 4.5 | 2020-06-04: 4.5
04Hyd09DS | 1.3 | 04Hyd09DS_1.3 | Drawings | Print | Printing of Construction Drawing | Urg&Imp | 2020-06-05 | 2020-06-05 | 2020-06-05 | Complete | Kabita Shrestha |  | 1 | bar: 2020-05-24 to 2020-05-29; 2020-05-31 to 2020-06-05; 2020-06-07 to 2020-07-18
04Hyd09DS | 1.4 | 04Hyd09DS_1.4 | Drawings | Drawing List | Construction Drawing List | Urg&Imp | 2020-06-05 | 2020-06-05 | 2020-06-05 | Complete | Kabita Shrestha |  | 2 | 2020-06-05: 2
04Hyd09DS | 1.5 | 04Hyd09DS_1.5 | Drawings | Review | Review of Drawings after Printing | Urg&Imp | 2020-06-05 | 2020-06-05 | 2020-06-05 | Complete | Kabita Shrestha |  | 1.5 | 2020-06-05: 1.5
04Hyd09DS | 1.6 | 04Hyd09DS_1.6 | Drawings | Internal Discuss/ Calcuation | Drawing Update and Bar Bending Schedule of Settling basin Panel 02 | Urg&Imp | 2020-06-08 |  |  | In Progress | Kabita Shrestha |  | 22 | 2020-06-08: 7; 2020-06-10: 3; 2020-06-11: 2.5; 2020-06-12: 2.5; 2020-06-14: 7
04Hyd09DS | 1.3 | 04Hyd09DS_1.3 | Drawings | Construction Drawings Check | Review of construction Drawing_ No.LEKHP_(00 to 11) / internal discussion | Urg&Imp | 2020-05-28 | 2020-05-28 | 2020-06-03 | Complete | Sabita Chimouriya |  | 8 | 2020-05-28: 3; 2020-05-31: 1; 2020-06-01: 1; 2020-06-02: 2.5; 2020-06-03: 0.5
04Hyd09DS | 1.3 | 04Hyd09DS_1.3 | Drawings | Construction Drawings Check | Review of construction Drawing_ weir and Undersluice _LEKHP-50-(C01-C12) | Urg&Imp | 2020-05-29 | 2020-05-29 | 2020-06-03 | Complete | Sabita Chimouriya |  | 16 | 2020-05-29: 6.5; 2020-05-31: 6; 2020-06-01: 2; 2020-06-02: 0.5; 2020-06-03: 1
04Hyd09DS | 1.3 | 04Hyd09DS_1.3 | Drawings | Construction Drawings Check | Review of construction Drawing_ Intake and Gravel Trap _LEKHP-51-(C01-C04 | Urg&Imp | 2020-05-30 | 2020-05-30 | 2020-06-03 | Complete | Sabita Chimouriya |  | 9 | 2020-06-01: 4; 2020-06-02: 3; 2020-06-03: 2
04Hyd09DS | 1.3 | 04Hyd09DS_1.3 | Drawings | Construction Drawings Check | Review of construction Drawing_ Settling Basin_LEKHP-53-(C01-C11) and Overall Longitudinal Profile | Urg&Imp | 2020-05-31 | 2020-05-31 | 2020-06-03 | Complete | Sabita Chimouriya |  | 3.5 | 2020-06-03: 3.5
04Hyd09DS | 1.3 | 04Hyd09DS_1.3 | Drawings | Rebar Drawings Check | Review of Reinforcement Drawing:Weir and flood wall | Urg&Imp | 2020-05-27 | 2020-05-27 | 2020-05-27 | Complete | Sabita Chimouriya |  | 1.5 | 2020-05-27: 1.5
04Hyd09DS | 1.3 | 04Hyd09DS_1.3 | Drawings | Rebar Drawings Check | Review of Reinforcement Drawing: Intake and Gravel Trap | Urg&Imp | 2020-05-24 | 2020-05-25 | 2020-05-25 | Complete | Sabita Chimouriya | 14 | 14 | 2020-05-24: 7; 2020-05-25: 7
04Hyd09DS | 1.3 | 04Hyd09DS_1.3 | Drawings | Rebar Drawings Check | Review of Reinforcement Drawing: Settling Basin_Panel-2 | Urg&Imp | 2020-05-26 | 2020-05-26 | 2020-05-26 | Complete | Sabita Chimouriya |  | 4 | 2020-05-26: 4
04Hyd09DS | 1.3 | 04Hyd09DS_1.3 | Drawings | Rebar Drawings Check | Review of Reinforcement Drawing: Settling Basin_Panel-3 | Urg&Imp | 2020-05-26 | 2020-05-26 | 2020-05-26 | Complete | Sabita Chimouriya |  | 4 | 2020-05-26: 3; 2020-05-27: 1
04Hyd09DS | 1.3 | 04Hyd09DS_1.3 | Drawings | Rebar Drawings Check | Reinforcement Drawing: Inlet Transition of Settling Basin | Urg&Imp | 2020-05-27 |  |  | Stopped | Sabita Chimouriya |  | 3 | 2020-05-27: 2; 2020-05-28: 1
04Hyd09DS | 1.3 | 04Hyd09DS_1.3 | Drawings | Literature Review/ Internal Discuss | Reinforcement Drawing: Inlet Transition of Settling Basin | Urg&Imp | 2020-05-27 |  |  | Stopped | Sabita Chimouriya |  | 4 | 2020-05-27: 2; 2020-05-28: 2
04Hyd09DS | 1.7 | 04Hyd09DS_1.7 | Drawings | Update/Correction/Final compilation | Final update weir and undersluice | Urg&Imp | 2020-06-07 | 2020-06-10 | 2020-06-10 | Complete | Sanish Maharjan |  | 20 | 2020-06-07: 6.5; 2020-06-08: 7; 2020-06-10: 6.5
04Hyd09DS | 1.8 | 04Hyd09DS_1.8 | Drawings | Update/Correction/Final compilation | Final update of Intake/ Gravel trap/ Flushing culvert/ Approach canal | Urg&Imp | 2020-06-11 | 2020-06-12 |  | In Progress | Sanish Maharjan |  | 16.5 | 2020-06-11: 6.5; 2020-06-12: 6; 2020-06-14: 4
04Hyd09DS | 1.9 | 04Hyd09DS_1.9 | Drawings | Update/Correction/Final compilation | Final update of spillway/Revision-03 |  | 2020-06-14 | 2020-06-14 | 2020-06-14 | Complete | Sanish Maharjan |  | 2.5 | 2020-06-14: 2.5
04Hyd09DS | 1.9 | 04Hyd09DS_1.9 | Drawings | Update/Correction/Final compilation | [8 empty] | 0
04Hyd09DS | 1.8 | 04Hyd09DS_1.8 | Drawings | Literature Review/ Internal Discuss/ Calcuation | Bar Bending Schedule ofCounterfort flood Wall | Urg&Imp | 2020-06-04 | 2020-06-05 | 2020-06-05 | Complete | Sabita Chimouriya |  | 11 | 2020-06-04: 6; 2020-06-05: 4; 2020-06-11: 1
04Hyd09DS | 1.9 | 04Hyd09DS_1.9 | Drawings | Literature Review/ Internal Discuss/ Calcuation | Bar Bending Schedule of flood Wall panel -2 | Urg&Imp | 2020-06-05 | 2020-06-07 | 2020-06-07 | Complete | Sabita Chimouriya |  | 6.5 | 2020-06-05: 3; 2020-06-07: 2; 2020-06-11: 1.5
04Hyd09DS | 2 | 04Hyd09DS_2 | Drawings | Literature Review/ Internal Discuss/ Calcuation | Bar Bending Schedule of flood Wall panel -3 | Urg&Imp | 2020-06-07 | 2020-06-07 | 2020-06-07 | Complete | Sabita Chimouriya |  | 7 | 2020-06-07: 5; 2020-06-11: 2
04Hyd09DS | 2 | 04Hyd09DS_2 | Drawings | Literature Review/ Internal Discuss/ Calcuation | Bar Bending Schedule of Weir and Stilling Basin | Urg&Imp | 2020-06-08 | 2020-06-10 | 2020-06-10 | Complete | Sabita Chimouriya |  | 21.5 | 2020-06-08: 7; 2020-06-09: 6.5; 2020-06-10: 6.5; 2020-06-11: 1.5
04Hyd09DS | 2 | 04Hyd09DS_2 | Drawings | Literature Review/ Internal Discuss/ Calcuation | Bar Bending Schedule of Gravel Trap | Urg&Imp | 2020-06-11 |  |  | Complete | Sabita Chimouriya |  | 6 | 2020-06-12: 6
04Hyd09DS | 1.3 | 04Hyd09DS_1.3 | Drawings | Construction Drawings Update | Update of Intake and Gravel Trap as per RS sir Comments-Rev-02 | Urg&Imp | 2020-05-24 | 2020-05-24 | 2020-05-24 | Complete | Sanish Maharjan |  | 7 | 2020-05-24: 7
04Hyd09DS | 1.5 | 04Hyd09DS_1.5 | Drawings | Construction Drawings Update | Update of Spillway and Gravel Flushing Culvert as per RS sir Comments-Rev-02 | Urg&Imp | 2020-05-25 | 2020-05-28 | 2020-05-28 | Complete | Sanish Maharjan |  | 4 | 2020-05-25: 2; 2020-05-28: 2
04Hyd09DS | 1.6 | 04Hyd09DS_1.6 | Drawings | Construction Drawings Update | Update drawing of Undersluice/weir/Spillway for structural analysis |  | 2020-06-09 | 2020-06-09 | 2020-06-09 | Complete | Sanish Maharjan |  | 7 | 2020-06-09: 7
04Hyd09DS | 1.6 | 04Hyd09DS_1.6 | Drawings | Construction Drawings Update | Update of Settling basin as per RS sir Comments-Rev-01 | Urg&Imp | 2020-05-25 | 2020-05-29 | 2020-05-29 | Complete | Sanish Maharjan |  | 13.5 | 2020-05-25: 4; 2020-05-27: 5; 2020-05-29: 4.5
04Hyd09DS | 1.7 | 04Hyd09DS_1.7 | Drawings | Construction Drawings Update | Update of Settling basin flushing canal as per RS sir Comments-Rev-02 |  |  |  |  | Complete | Sanish Maharjan |  | 6 | 2020-06-04: 6
04Hyd09DS | 1.8 | 04Hyd09DS_1.8 | Drawings | Construction Drawings Update | Creating new sections in Settling Basin (settling zone) as per RS sir Comments-Rev-01 | Urg&Imp | 2020-05-26 | 2020-05-26 | 2020-05-26 | Complete | Sanish Maharjan |  | 7 | 2020-05-26: 7
04Hyd09DS | 1.9 | 04Hyd09DS_1.9 | Drawings | Construction Drawings/ Rebar Drawing | Creating new sections in Settling Basin (Inlet zone) for construction and reinforcement drawing | Urg&Imp | 2020-05-28 | 2020-05-28 | 2020-05-29 | Complete | Sanish Maharjan |  | 6.5 | 2020-05-28: 4; 2020-05-29: 2.5
04Hyd09DS | 2 | 04Hyd09DS_2 | Design/Analysis/Annexes | Cost Estimation update | Cost estimation update as per updated drawings of Intake,GT, Spillway & Settling Basin | Urg&Imp | 2020-05-31 | 2020-05-31 | 2020-05-31 | Complete | Sanish Maharjan |  | 2 | 2020-05-31: 2
04Hyd09DS | 2.1 | 04Hyd09DS_2.1 | Design/Analysis/Annexes | Cost Estimate Underground Works | Inlet and outlet portal of HRT | Urg&Imp | 2020-05-24 | 2020-05-24 | 2020-05-24 | Complete | Surendra Shrestha |  | 3 | 2020-05-24: 3
04Hyd09DS | 2.2 | 04Hyd09DS_2.2 | Design/Analysis/Annexes | Cost Estimate Underground Works | HRT Cost estimate | Urg&Imp | 2020-05-24 | 2020-05-25 | 2020-05-25 | Complete | Surendra Shrestha |  | 4 | 2020-05-24: 4
04Hyd09DS | 2.3 | 04Hyd09DS_2.3 | Design/Analysis/Annexes | Cost Estimate Underground Works | HRT Cost estimate | Urg&Imp | 2020-05-25 | 2020-05-25 | 2020-05-25 | Complete | Surendra Shrestha |  | 5 | 2020-05-25: 5
04Hyd09DS | 2.4 | 04Hyd09DS_2.4 | Design/Analysis/Annexes | Cost Estimate Underground Works | Vetn tunnel ,Vent Tunnel portal | Urg&Imp | 2020-05-25 | 2020-05-25 | 2020-05-25 | Complete | Surendra Shrestha |  | 2 | 2020-05-25: 2
04Hyd09DS | 2.5 | 04Hyd09DS_2.5 | Design/Analysis/Annexes | Cost Estimate Underground Works | Surge Shaft | Urg&Imp | 2020-05-26 | 2020-05-26 | 2020-05-26 | Complete | Surendra Shrestha |  | 4 | 2020-05-26: 4
04Hyd09DS | 2.6 | 04Hyd09DS_2.6 | Design/Analysis/Annexes | Cost Estimate Underground Works | Cost Summary | Urg&Imp | 2020-05-26 | 2020-05-26 | 2020-05-26 | Complete | Surendra Shrestha |  | 3 | 2020-05-26: 3
04Hyd09DS | 2.7 | 04Hyd09DS_2.7 | Design/Analysis/Annexes | Cost Estimate Underground Works | Cost estimation review | Urg&Imp | 2020-05-27 | 2020-05-27 | 2020-05-27 | Complete | Surendra Shrestha |  | 13 | 2020-05-27: 3; 2020-05-28: 3; 2020-05-29: 7
04Hyd09DS | 2.8 | 04Hyd09DS_2.8 | Design/Analysis/Annexes | Cost Estimate Underground Works | Comparison of estimated cost with tender cost | Urg&Imp | 2020-05-27 | 2020-05-27 | 2020-05-27 | Complete | Surendra Shrestha |  | 7 | 2020-05-27: 4; 2020-05-28: 3
02Hyd09DS | 2.9 | 02Hyd09DS_2.9 | Review | Expansion Joint Drawings | Review of the Expansion Joint Drawings | Urg&Imp | 2020-05-27 | 2020-05-27 | 2020-05-27 | Complete | Ishwar Dahal |  | 5 | 2020-05-27: 5
02Hyd09DS | 2.1 | 02Hyd09DS_2.1 | Drawings | Update/check | Update in final tender drawings | Urg&Imp | 2020-06-05 | 2020-06-05 | 2020-06-05 | Complete | Sanish Maharjan |  | 5 | 2020-06-05: 5
04Hyd09DS | 3 | 04Hyd09DS_3 | Review | Coordination with Team Members | Regardign Drawings and Annexes | Urg&Imp | 2020-05-27 |  |  | In Progress | Ishwar Dahal |  | 11 | 2020-05-27: 2; 2020-05-28: 4; 2020-05-31: 5
04Hyd09DS | 3.1 | 04Hyd09DS_3.1 | Design/Analysis/Annexes | Structural Analysis: Headpond |  | Urg&Imp | 2020-05-24 |  |  | In Progress | Anish Shakya |  | 0
04Hyd09DS | 3.2 | 04Hyd09DS_3.2 | Review | Annexes Review | HW Design Review | Urg&Imp |  |  |  | In Progress | Ishwar Dahal |  | 5 | 2020-05-28: 3; 2020-05-31: 2
02Hyd09DS | 3.3 | 02Hyd09DS_3.3 | Review | Stability Analysis | Learning/review sability analysis of Flood wall | Imp&Not-Urg | 2020-05-31 |  |  | In Progress | Sanish Maharjan |  | 8 | 2020-05-31: 3; 2020-06-01: 5
01Hyd09FS | 3.4 | 01Hyd09FS_3.4 | Review | Print | Printing of Final DPR | Urg&Imp | 2020-06-02 |  |  | Complete | Sanish Maharjan |  | 12 | 2020-06-02: 6; 2020-06-03: 6
02Hyd09DS | 3.5 | 02Hyd09DS_3.5 | Review | Drawing review | Headworks | Urg&Imp | 2020-05-31 | 2020-05-31 | 2020-05-31 | Complete | Surendra Shrestha |  | 3 | 2020-05-31: 3
02Hyd09DS | 3.6 | 02Hyd09DS_3.6 | Drawings | SOP | Headworks | Imp&Not-Urg | 2020-05-31 |  |  | In Progress | Surendra Shrestha |  | 4 | 2020-05-31: 4
02Hyd09DS | 3.7 | 02Hyd09DS_3.7 | Drawings | SOP | Headworks | Imp&Not-Urg | 2020-05-31 | 2020-06-01 | 2020-06-01 | Complete | Surendra Shrestha |  | 7 | 2020-06-01: 7
01Hyd09FS | 3.8 | 01Hyd09FS_3.8 | Report Writing | Print | Printing of Final DPR | Urg&Imp | 2020-06-01 | 2020-06-05 |  | In Progress | Surendra Shrestha |  | 6 | 2020-06-02: 6
01Hyd09FS | 3.9 | 01Hyd09FS_3.9 | Report Writing | Print | Printing of Final DPR | Urg&Imp | 2020-06-01 |  |  | In Progress | Surendra Shrestha |  | 7 | 2020-06-03: 7
02Hyd04FS | 3.1 | 02Hyd04FS_3.1 | Report Writing | Print | Printing of Tender documents and drawings | Urg&Imp | 2020-06-04 | 2020-06-04 | 2020-06-04 | Complete | Surendra Shrestha |  | 6 | 2020-06-04: 6
02Hyd11FS | 2.2 | 02Hyd11FS_2.2 | Report Writing | Print | Printing of Tender documents and drawings |  | 2020-06-05 | 2020-06-05 | 2020-06-05 | Complete | Surendra Shrestha |  | 4 | 2020-06-04: 1; 2020-06-05: 3
02Hyd05FS | 2.3 | 02Hyd05FS_2.3 | Report Writing | Print | Printing of Tender documents and drawings | [5 empty] | Surendra Shrestha |  | 4 | 2020-06-05: 4
#N/A | 4 | #N/A |  | Update of Files from Computer/ Compilation to Engineering Drive | Completed from Project ID 01 to ID 10 | Imp&Not-Urg | 2020-06-01 | 2020-06-05 |  | In Progress | Ishwar Dahal |  | 9 | 2020-06-01: 3; 2020-06-02: 2; 2020-06-04: 4
01Hyd09FS | 4.1 | 01Hyd09FS_4.1 | Report Writing | Print and Checking | Printing of Final DPR | Urg&Imp | 2020-06-01 | 2020-06-01 |  | In Progress | Ishwar Dahal |  | 7 | 2020-06-01: 2; 2020-06-02: 2; 2020-06-04: 3
04Hyd09DS | 2.4 | 04Hyd09DS_2.4 | Review | meeting | Internal coordination meeting | Urg&Imp | 2020-06-05 | 2020-06-05 | 2020-06-05 | Complete | Sanish Maharjan |  | 1 | bar: 2020-05-24 to 2020-05-29; 2020-05-31 to 2020-06-05; 2020-06-07 to 2020-07-18
04Hyd09DS | 2.5 | 04Hyd09DS_2.5 | Review | meeting | Internal coordination meeting | Urg&Imp | 2020-06-05 | 2020-06-05 | 2020-06-05 | Complete | Ishwar Dahal |  | 2 | 2020-06-05: 2
04Hyd09DS | 2.6 | 04Hyd09DS_2.6 | Design/Analysis/Annexes | Annexes | Annex A: Hydraulic Calculations, Review and Update | Urg&Imp | 2020-06-07 | 2020-06-07 | 2020-06-07 | Complete | Ishwar Dahal |  | 7 | 2020-06-05: 5; 2020-06-07: 2
02TrL07FS | 2.7 | 02TrL07FS_2.7 | Drawings | Print | Printing of Tender documents and drawings | Urg&Imp | 2020-06-07 | 2020-06-07 | 2020-06-07 | Complete | Surendra Shrestha |  | 3 | 2020-06-07: 3
02Hyd06FS | 2.8 | 02Hyd06FS_2.8 | Drawings | Print | Printing of Tender documents and drawings | Urg&Imp | 2020-06-07 | 2020-06-07 | 2020-06-07 | Complete | Surendra Shrestha |  | 3.5 | 2020-06-07: 3.5
#N/A | 2.9 | #N/A | [8 empty] | Surendra Shrestha |  | 0 | bar: 2020-06-08
#N/A | 3 | #N/A | [8 empty] | Surendra Shrestha |  | 0 | bar: 2020-05-24 to 2020-05-29; 2020-05-31 to 2020-06-05; 2020-06-07 to 2020-07-18
04Hyd09DS | 3.1 | 04Hyd09DS_3.1 | Drawings | Literature Review/ Internal Discuss/ Calcuation | Bar Bending Schedule of Intake and gravel trap and reinforcement drawing correction | Urg&Imp | 2020-06-10 |  |  | In Progress | Surendra Shrestha |  | 7 | 2020-06-10: 7
04Hyd09DS | 3.2 | 04Hyd09DS_3.2 | Drawings | Literature Review/ Internal Discuss/ Calcuation | Bar Bending Schedule of Intake and gravel trap and reinforcement drawing correction | Urg&Imp | 2020-06-10 |  |  | In Progress | Surendra Shrestha |  | 7 | 2020-06-11: 7
04Hyd09DS | 3.3 | 04Hyd09DS_3.3 | Drawings | Literature Review/ Internal Discuss/ Calcuation | Bar Bending Schedule of Intake and gravel trap and reinforcement drawing correction | Urg&Imp | 2020-06-10 |  |  | In Progress | Surendra Shrestha |  | 5 | 2020-06-12: 5
04Hyd09DS | 3.4 | 04Hyd09DS_3.4 | Drawings | Literature Review/ Internal Discuss/ Calcuation | Reinforcement drawing elevation intake | Urg&Imp | 2020-06-10 |  |  | In Progress | Surendra Shrestha |  | 4 | 2020-06-12: 2; 2020-06-14: 2
04Hyd09DS | 3.4 | 04Hyd09DS_3.4 | Drawings | Literature Review/ Internal Discuss/ Calcuation | Reinforcement drawing intake-section | Urg&Imp | 2020-06-14 |  |  | In Progress | Surendra Shrestha |  | 4.5 | 2020-06-14: 4.5
04Hyd09DS | 3.5 | 04Hyd09DS_3.5 | Review | Check and Update of Cost Estimate, HW | Revision of Cost Estimate of Headworks | Urg&Imp | 2020-06-07 | 2020-06-07 | 2020-06-07 | Complete | Ishwar Dahal |  | 4 | 2020-06-07: 4
#N/A | 3.6 | #N/A | Review | Meeting | Structural Design Discussion of LEKHP and SGHP | Urg&Imp | 2020-06-07 | 2020-06-07 | 2020-06-07 | Complete | Ishwar Dahal |  | 1 | bar: 2020-06-07
04Hyd09DS | 3.7 | 04Hyd09DS_3.7 | Design/Analysis/Annexes | Stability analysis | Stability analysis of settling basin panel 4 and d5 |  | 2020-05-27 | 2020-06-07 | 2020-06-07 | Complete | Anish Shakya |  | 18 | 2020-05-27: 3; 2020-05-30: 3; 2020-06-06: 4; 2020-06-07: 8
| 3.8 | _3.8 |  | Structural analysis: settling basin | Structural analysis of settling basin panel 4 and 5 |  | 2020-06-07 | 2020-06-14 |  | In Progress | Anish Shakya | 14 | 0
04Hyd09DS | 3.9 | 04Hyd09DS_3.9 | Review | Annex review and Update | Underground Annex_Hydraulics, Structure Compilation and Update | Urg&Imp | 2020-06-09 | 2020-06-09 | 2020-06-09 | Complete | Ishwar Dahal |  | 7 | 2020-06-08: 7
04Hyd09DS | 4 | 04Hyd09DS_4 | Review | Coordination for Structural Analysis | Coordination in between Suman, Deepesh and Anish Dai |  | 2020-06-10 | 2020-06-12 |  | Complete | Ishwar Dahal |  | 4 | 2020-06-10: 4
09Hyd02FS | 4.1 | 09Hyd02FS_4.1 | Review | Print for Submission to Client | Print of one Copy of Final FSR | Imp&Not-Urg | 2020-06-10 | 2020-06-10 | 2020-06-10 | Complete | Ishwar Dahal |  | 1 | bar: 2020-05-24 to 2020-05-29; 2020-05-31 to 2020-06-05; 2020-06-07 to 2020-07-18
04Hyd09DS | 4.2 | 04Hyd09DS_4.2 | Review | Discussion regarding BBS and Rebar Drawings | Update and Discussion in Gravel Trap and Side Spillway | Urg&Imp | 2020-06-10 |  |  | In Progress | Ishwar Dahal |  | 1 | bar: 2020-06-11
04Hyd09DS | 4.3 | 04Hyd09DS_4.3 | Review | Review of Rebar and BBS Drawing_Counterfort Floodwall | Update and Review of works by Sabita for Rebar and BBS of Counterfort | Urg&Imp | 2020-06-12 | 2020-06-12 | 2020-06-12 | In Progress | Ishwar Dahal |  | 4 | 2020-06-12: 4
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
|  | _ | [10 empty] | 0
Note on V1: ====== ID#AAAAJmuH2m0 Sunil Ghaju (2020-06-01 02:52:38) +sabita.chimouriya@eimaven.com.np +surendra.shrestha@eimaven.com.np reminder for timely updates _Assigned to Sabita Chimouriya_
Note on W1: ====== ID#AAAAJxS6HW4 Sunil Ghaju (2020-06-02 04:56:11) +sanish.maharjan@eimaven.com.np reminder for timely update _Assigned to you_
Note on X1: ====== ID#AAAAJoPcLAI Sunil Ghaju (2020-06-03 05:03:36) +surendra.shrestha@eimaven.com.np +sanish.maharjan@eimaven.com.np +ishwar.dahal@eimaven.com.np Reminder for your input
Note on I15: ====== ID#AAAAJmF3Nr4 Sunil Ghaju (2020-05-27 05:56:40) +kabita.shrestha@eimaven.com.np please try to fill the estimated completion date for every activities _Assigned to Kabita Shrestha_
Note on F19: ====== ID#AAAAJm6H9C4 Sunil Ghaju (2020-05-29 04:47:57) +kabita.shrestha@eimaven.com.np please mention the drawings name as indicated earlier _Assigned to Kabita Shrestha_
Note on F25: ====== ID#AAAAJxS6HXE Sunil Ghaju (2020-06-02 04:59:20) +kabita.shrestha@eimaven.com.np please clarify the drawings no. or section _Assigned to Kabita Shrestha_
Note on F33: ====== ID#AAAAJnYMdcY Sunil Ghaju (2020-05-31 05:09:48) +sabita.chimouriya@eimaven.com.np please mention the complete drawings nos. (LEKHP_53_C01-C06 for example) _Assigned to Sabita Chimouriya_ ------ ID#AAAAJnC4Pfw Sabita Chimouriya (2020-05-31 05:49:03) drawing number is varies according to the chapter..so it is difficult to write every drawing no. so i just write the chapter number ------ ID#AAAAJnC4Pgo Sunil Ghaju (2020-05-31 06:16:57) ok
Note on S37: ====== ID#AAAAJmFTw3s Sunil Ghaju (2020-05-28 04:47:29) +sabita.chimouriya@eimaven.com.np for 27th May? _Assigned to Sabita Chimouriya_
Note on F38: ====== ID#AAAAJkirTTU Sunil Ghaju (2020-05-26 13:29:06) +sabita.chimouriya@eimaven.com.np it is better if you breakdown your activity based on drawings nos. _Assigned to Sabita Chimouriya_
Note on L40: ====== ID#AAAAJmF3Nq0 Sunil Ghaju (2020-05-27 05:37:41) +kabita.shrestha@eimaven.com.np +ishwar.dahal@eimaven.com.np +sabita.chimouriya@eimaven.com.np is this assign to Sabita? _Assigned to Kabita Shrestha_ ------ ID#AAAAJmF3Nwk Kabita Shrestha (2020-05-27 06:46:17) yes

## Team
Employee ID | Name | Email | Phone-1 | Phone-2 | Team | Picture URL
072-73-01 | Sunil Ghaju | ghajusunil@gmail.com | 9851157962 | 9841377853 | Mgt
074-75-01 | Ishwar Dahal | ishwar.dahal@eimaven.com.np | 9861603169 | 9808682743 | Prj_Eng
076-77-02 | Anish Shakya | anish.shakya@eimanve.com.np |  |  | Prj_Eng
075-76-01 | Surendra Shrestha | surendra.shrestha@eimaven.com.np |  |  | Eng
076-77-01 | Kabita Shrestha | kabita.shrestha@eimaven.com.np |  |  | Prj_Eng
075-76-02 | Sanish Maharjan | sanish.maharjan@eimaven.com.np | 9843416915 | 9808012905 | Eng
075-76-03 | Sabita Chimouriya | sabita.chimouriya@eimaven.com.np | 9860656978 |  | Eng
075-76-04 | Uttam Shrestha | uttam.shrestha@eimvaven.com.np |  |  | Adm
072-73-02 | Bina Sahukhal | bina.sahukhal@gmail.com | 9841377853 | 9851157962 | Acc

## Status
Status ID | Status Image | Sort
Planned |  | 1
Assigned |  | 2
In Progress |  | 3
Stopped |  | 4
Sent for External Review |  | 5
Complete |  | 6

## Level of Study
Level of Study | Level of Study_ID
Desk_Study | 00
Pre_Feasibility | 01
Feasibility | 02
Updated_Feasibility | 03
Tender_Document_Civil | 04
Tender_Document_EM | 05
Tender_Document_HM | 06
Tender_Document_TL | 07
Tender_Document_Site_Facilities | 08
Detail Design/Detail Project Report | 09
Due Diligence Study | 10
Tender_Document_Project Road | 11
Asset Valuation | 12
Bid Evaluation | 13
Project Managment and Construction Supervisoin | 14

## Key Mile Stone
2020-04-01
Project | Week 15 | Week- 16 | Week 17 | Week 18 | Remarks
02H04-Planned | Tender Drawings and BOQ ready for Submission | Complete Set of Tender Documents for Civil Work_Lot03 | Complete Set of Tender Documents (Lot 02: Project Road | Complete Set of Tender Documents (Lot 04: EM Works)
02H04-Progress | Completed except PH and Pipe Crossing related works | Completed except PH and Pipe Crossing related works | Completed | Completed | Progress on tender documents has been late due to NLHP DPR Submission and other update on PH Drawings
02H09-Planned |  |  | Tunnel Alignment and Tunnel Portals Finalization | Detail Planning for Draft DED Report Preparation
02H09-Progress |  |  | No progress due to works on Tender Works | No progress due to works on Tender Works
04H09-Planned | Annex-C and D Preparation | Reinforcement drawings,Annex Preparation | Underground works Estimation | Underground works Estimation and Penstock alignmnet Finalization
04H09-Progress | Done Estimation and need to compile the remaining calculation after analysis | Prepared annex and Compiled files | No progress due to the correction in construction drawings as per comments and futher improvement of report(Annex B-1and B-2) | No progress due to the correction in construction drawings as per comments and futher improvement of report(Annex B-1) | Reinforement drawing can be done after analysis and penstock alignmnet can be finalized after pitting
12J09-Planned | Remaining structural analysis (spillway crest, d/s floodwall, trunnion block), final drawings, Report preparation | Final drawings, Report preparation, Cost estimation | Structural analysis (spillway crest, trunnion block), Final drawings, cost estimation, temperature control of mass concrete | Final drawings, cost estimation submit to Narayan Sir, Final report | Construction Planning, Instrumentation (Can be done only when lockdown ends and input from Narayan Sir is available), dam breach analysis (can be done only when lockdown ends and file in office is accessible)
12J09-Progress | Structural design of floodwall, reinforcement drawing and update of construction drawing | Structural design of floodwall (the time estimated exceeded for structural design of floodwall as it was a counterfort floodwall and not a simple cantilever floodwall as it was previously thought, Report preparation, Reinforcement drawing, update of construction drawing, submission of report, construction and reinforcement drawing | Review of construction drawing, structural design of spillway crest and energy dissipator, revision of placement of contraction joint, reinforcement drawing, update of construction drawing, cost estimation | Structural design of energy dissipator, review of reinforcement drawing, stability analysis of updated shape of spillway given by Hydraulics team, cost estimation
2020-05-01
Project | Week 19 | Week 20 | Week 21 | Week 22 | Remarks
02H04-Planned | Complete Set of Tender Documents (Lot 05: HM Works) | Complete Set of Tender Documents (Lot 06: TL Works)
02H04-Progress | Completed | Completed |  |  | Tender Documents Completed except for the Overhead Pipe Crossing Design, Drawings and BoQ update based on it
02H09-Planned |  |  | Tunnel Alignment and Tunnel Portals Finalization Annex Preparation for Draft DPR | Detail Planning for Draft DED Report Preparation Annex for Draft DPR | Review from Expert will be helpful to start DPR
02H09-Progress |  |  | Ongoing and shall be finalized with discussion to expert | Shall be finalized in coordination with Client
04H09-Planned | Review and Compile Vol-B(presentation can be improved) and improvement in report annex B-1and updates the drawings as per comments(if any) | Check the quantity and make comparative sheets with tender and the remaining part in annex (if analysis completes) | Reinforcement drawings of headpond,setlling basin and Flush of gravel trap and Settling basin | Finalize report and drawings
04H09-Progress
12J09-Planned | Finalize cost estimation, make corrections in construction and reinforcement drawings, do remaining reinforcement drawings, work on temperature control of mass concrete, instrumentation, trunnion block design | Finalize report and drawings and send to Nawin Sir and Narayan Sir for approval, Finalize remaining things in report, Construction planning, update drawing and report as per Nawin Sir and Narayan sir comments (if any) | Construction planning, Finalize drawings and report after Nawin Sir and Narayan Sir comments (if any)
12J09-Progress | Cost estimation- complete, temperature control of mass concrete - complete, instrumentation report - complete, Final report submission, construction planning -almost complete (need to put some drawings), Construction drawing -complete
13H10-Planned | Review of FSR Report and Review Report of FSR | Independent Hydrological Analysis Calculation and Report | Review of FSR Cost and Independent Cost Estimate | Deisgn Review and DDS Report Works
13H10-Progress | Completed | Completed, Review of Analysis and Report Remaining | Completed, Completed Set of Drawings not available | Draft Report Prepared, however design check yet remaining
2020-06-01
Project | Week 23 | Week 24 | Week 25 | Week 26 | Remarks
Note on D5: ====== ID#AAAAJlCpkrA (2020-05-22 06:49:15) +kabita.shrestha@eimaven.com.np This has already completed. Isn't it? What are the key tasks in this part?? Please list the task for this assignment. _Assigned to Kabita Shrestha_ -Sunil Ghaju I dont know who arranged this..This one is the milestone of Suni Gad Hydropower Project.. I wrote it down yesterday.. -Ishwar Dahal
Note on E5: ====== ID#AAAAJlCpkqg (2020-05-22 06:49:15) +kabita.shrestha@eimaven.com.np Can you explain this part?? _Assigned to Kabita Shrestha_ -Sunil Ghaju I dont know who arranged this..This one is the milestone of Suni Gad Hydropower Project.. I wrote it down yesterday.. -Ishwar Dahal
Note on A8: ====== ID#AAAAJlCpkq4 (2020-05-22 06:49:15) +kabita.shrestha@eimaven.com.np Can you manage some time to update the progress in our planned schedule? _Assigned to Kabita Shrestha_ -Sunil Ghaju
Note on B9: ====== ID#AAAAJlCpkrE (2020-05-22 06:49:15) +anish.shakya@eimaven.com.np can you please update key milestones for JIRI Project?? _Assigned to Anish Shakya_ -Sunil Ghaju
Note on A10: ====== ID#AAAAJlCpkqo (2020-05-22 06:49:15) +anish.shakya@eimaven.com.np Can you manage some time to update the progress for Jiri works _Assigned to Anish Shakya_ -Sunil Ghaju
Note on B14: ====== ID#AAAAJmF3NtI Sunil Ghaju (2020-05-27 06:01:07) +ishwar.dahal@eimaven.com.np +kabita.shrestha@eimaven.com.np +anish.shakya@eimaven.com.np Dear all, reminder to update the progress for month of May 2020 and prepare plan for June 2020
Note on B20: ====== ID#AAAAJlCpkqs (2020-05-22 06:49:15) +kabita.shrestha@eimaven.com.np Don't merge cell, use text wrapping _Assigned to Kabita Shrestha_ -Sunil Ghaju
Note on C20: ====== ID#AAAAJlCpkqk (2020-05-22 06:49:15) +kabita.shrestha@eimaven.com.np use text wrapping _Assigned to Kabita Shrestha_ -Sunil Ghaju +kabita.shrestha@eimaven.com.np Does it take week to make a comparative analysis when you already have quantities for both phases? Please review your weekly targets and update accordingly. -Sunil Ghaju
Note on D20: ====== ID#AAAAJlCpkqw (2020-05-22 06:49:15) +kabita.shrestha@eimaven.com.np use text wrapping _Assigned to Kabita Shrestha_ -Sunil Ghaju
Note on B22: ====== ID#AAAAJlCpkq8 (2020-05-22 06:49:15) +ishwar.dahal@eimaven.com.np can you please update planning regarding dam breach analysis and hydraulic work if any, and any other things as you feel necessary in what I have written. _Assigned to Ishwar Dahal_ -Anish Shakya +sabita.chimouriya@eimaven.com.np plz inform me if there is any changes that needs to be made in the planning...if you need more time for a particular work. _Reassigned to Sabita Chimouriya_ -Anish Shakya Now i m working on Cost estimation ..so after its completion only ..i ll work on the drawings part. -Sabita Chimouriya ok -Anish Shakya
Note on A24: ====== ID#AAAAJlCpkq0 (2020-05-22 06:49:15) Hongu A DDS Report -Sunil Ghaju

## Sector
Sector | Initials
Energy | Eng
Hydropower | Hyd
Transmission Line | TrL
Water Resources | WaR
Trasportation | Tra
Infrastructure Development | InD

## Deliverables
Project Name | Sector | Deliverables & Level of Study | Submission Stage | Deliverables
Nupche_Likhu_HPP | Hydropower | Bid Evaluation | FS | 01Hyd13FS
Suni_Gad_HPP | Hydropower | Detail Design/Detail Project Report | DS | 02Hyd09DS
Suni_Gad_HPP | Hydropower | Tender_Document_Civil | FS | 02Hyd04FS
Suni_Gad_HPP | Hydropower | Tender_Document_EM | FS | 02Hyd05FS
Suni_Gad_HPP | Hydropower` | Tender_Document_HM | FS | #N/A
Suni_Gad_HPP | Transmission Line | Tender_Document_TL | FS | 02TrL07FS
DPR Preparation of a Dam & an Arificial Lake in Jiri Municipality | Hydropower | Detail Design/Detail Project Report | FS | 12Hyd09FS
Lower_Erkhuwa_HPP | Hydropower | Detail Design/Detail Project Report | DS | 04Hyd09DS
Suni_Gad_HPP | Hydropower | Tender_Document_Project Road | FS | 02Hyd11FS
Administrative Task | Hydropower | Desk_Study | DS | #N/A
Upper Myagdi HPP | Hydropower | Feasibility | FS | 09Hyd02FS
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## Project
Project | Project ID
Administrative Task | 00
Nupche_Likhu_HPP | 01
Suni_Gad_HPP | 02
Doodhpokhari_Chepe_HPP | 03
Lower_Erkhuwa_HPP | 04
Hadi Khola HPP | 05
Upper Lohare Khola HPP | 06
Upper Phawa Khola HPP | 07
Lankhuwa Khola SHPP | 08
Upper Myagdi HPP | 09
Mid Hongu B HPP | 10
Seti Khola Small Hydroelectric Project | 11
DPR Preparation of a Dam & an Arificial Lake in Jiri Municipality | 12
Mid Hongu A HPP | 13
Myagdi Khola HPP_Hydrological Stud | 14
Jhyadi Khola Hydropower Project | 15

## Guidelines to Create Activities
S.N | Rules
1 | Activity code shall start with project ID (two digit) + Project Type (three alphabet) + Level of Study (two digit)
2 | Activities related to drawings shall be clearly identifiable based on structure type and standard structure code shall be mentioned
3 | Any activity taking equal to or more than 3.5 hours shall be clearly mentioned and should not be vegue
Note on B4: ====== ID#AAAAJk_FGwM Sunil Ghaju (2020-05-26 03:22:43) +surendra.shrestha@eimaven.com.np please breakdown activities according the rule mentioned _Assigned to Surendra Shrestha_

## File Management System
E.I Maven Pvt. Ltd.
File Management/Naming System
List of Project |  |  |  | Hydropower | H
S.N | Project Name | Project ID |  | Transmission Line | T
1 | Nupche_Likhu_HPP | 01 |  | Hydromechanical | M
2 | Suni_Gad_HPP | 02 |  | Electromechanical | E
3 | Doodhpokhari_Chepe_HPP | 03 |  | Site Facilities | F
4 | Lower_Erkhuwa_HPP | H
5 | Hadi Khola HPP | 05
6 | Upper Lohare Khola HPP | 06 |  | Level of Study
7 | Upper Phawa Khola HPP | 07 |  | Desk_Study | 00
8 | Lankhuwa Khola SHPP | 08 |  | Pre_Feasibility | 01
9 | Upper Myagdi HPP | 9 |  | Feasibility | 02
10 | Mid Hongu B HPP | 10 |  | Updated_Feasibility | 03
11 | Seti Khola Small Hydroelectric Project | 11 |  | Tender_Document_Civil | 04
12 | DPR Preparation of a Dam & an Arificial Lake in Jiri Municipality | 12 |  | Tender_Document_EM | 05
13 | Mid Hongu A HPP | 13 |  | Tender_Document_HM | 06
14 | Myagdi Khola HPP_Hydrological Stud | 14 |  | Tender_Document_TL | 07 | NLHP_Detail Design
15 | Jhyadi Khola Hydropower Project | 15 |  | Tender_Document_Site_Facilities | 08 | 01
|  |  |  | Detail Design | 09 | 01H09
|  |  |  | Due Diligence Study | 10 | 01H09_Hydraulic Design
|  |  |  | Tender_Document_Project Road | 11 | 01H09_Report
|  |  |  | Asset Valuation | 12
KEY Activity Codes | Devliverables
Submission Phase
Inernal_Rev
Draft Submission
Final Submisison
IR01 | IR01 Represents 1st revision |  | IR00 Represents 1st print for internal use/No revision
DS01 | DS01 Represents 2nd submission/1st revision |  | DS00 Represents 1st submission/No revision
FS01 | FS01 Represents 2nd submission/1st revision |  | FS01 Represents 1st submission/No revision
Example Folder File Name
1. There shoud be one main floder in server for single project
2. There immediate subfolder/file name shoud be named with ProjectIP_Type_Level of Study